## Sheet1
ITSC-3155 Software Engineering
Product Backlog
Feature Name | PRIORITY | POINTS | DEFINE USER STORY | ASSIGNED TO SPRINT | SPRINT #
Guest checkout (name/phone/address per order) | High | 8 | Yes | Yes | 1
Browse menu with categories & filters | High | 8 | Yes | Yes | 1
Menu management (create/edit dishes) | High | 13 | Yes | Yes | 1
Dish details: ingredients, price, calories | High | 8 | Yes | Yes | 1
Place order: takeout vs delivery | High | 5 | Yes | Yes | 2
Order tracking number generation | High | 3 | Yes | Yes | 2
Real-time order status tracking by order # | High | 8 | Yes | Yes | 2
Payment processing (multiple methods) | High | 13 | Yes | Yes | 3
Staff views for order management | Medium | 8 | Yes | Yes | 3
Chef/kitchen view for incoming orders | Medium | 5 | Yes | Yes | 3
Customer reviews & ratings | Medium | 8 | Yes | No | 4
Promotions & promo code generation | Medium | 8 | Yes | No | 4
Analytics: trends, preferences, sales | Low | 13 | Yes | No | 5
Documentation & staff training materials | Low | 5 | Yes | No | 5