## Sheet1
ITSC-3155 Software Engineering
User Stories
ID | FEATURE | AS A <type of user> | I WANT TO <perform some task> | SO THAT <achieve some goal> | FINAL STORY | PRIORITY | STORY POINT
1.0 | Guest checkout (name/phone/address per order) | Guest customer | place an order without creating an account | I can order quickly with minimal friction | As a Guest customer I want to place an order without creating an account so that I can order quickly with minimal friction | High | 5
2.0 | Guest checkout (name/phone/address per order) | Guest customer | enter my name, phone number, and address during checkout | the restaurant can contact me and deliver my order correctly | As a Guest customer I want to enter my name, phone number, and address during checkout so that the restaurant can contact me and deliver my order correctly | High | 3
3.0 | Browse menu with categories & filters | Customer | browse the menu by category (spicy, kids, vegetarian, low fat, etc.) | I can find items that match my preferences | As a Customer I want to browse the menu by category (spicy, kids, vegetarian, low fat, etc.) so that I can find items that match my preferences | High | 5
4.0 | Dish details: ingredients, price, calories | Customer | see ingredients, price, and calories for a dish | I can make informed choices before ordering | As a Customer I want to see ingredients, price, and calories for a dish so that I can make informed choices before ordering | High | 5
5.0 | Menu management (create/edit dishes) | Restaurant manager | create and update menu items and their details | the online menu stays accurate over time | As a Restaurant manager I want to create and update menu items and their details so that the online menu stays accurate over time | High | 8
6.0 | Place order: takeout vs delivery | Customer | choose takeout or delivery for my order | I can receive food in the way I prefer | As a Customer I want to choose takeout or delivery for my order so that I can receive food in the way I prefer | High | 3
7.0 | Order tracking number generation | Customer | receive an order tracking number after checkout | I can track my order status later | As a Customer I want to receive an order tracking number after checkout so that I can track my order status later | High | 2
8.0 | Real-time order status tracking by order # | Customer | check my order status using my order number | I know when it is being prepared and when it will be ready | As a Customer I want to check my order status using my order number so that I know when it is being prepared and when it will be ready | High | 5
9.0 | Staff views for order management | Staff member | view and manage incoming orders in an operational dashboard | we reduce errors and process orders efficiently | As a Staff member I want to view and manage incoming orders in an operational dashboard so that we reduce errors and process orders efficiently | Medium | 8
10.0 | Chef/kitchen view for incoming orders | Chef | see a kitchen-friendly view of orders with needed items and quantities | I can prepare orders faster with fewer mistakes | As a Chef I want to see a kitchen-friendly view of orders with needed items and quantities so that I can prepare orders faster with fewer mistakes | Medium | 5
11.0 | Payment processing (multiple methods, transaction status, failures) | Customer | pay using different payment methods and see whether my payment succeeded or failed | I can complete checkout and know if I need to retry | As a Customer I want to pay using different payment methods and see whether my payment succeeded or failed so that I can complete checkout and know if I need to retry | High | 8
12.0 | Customer reviews & ratings (one review per order) | Customer | leave at most one rating and review for my completed order | the restaurant gets clear feedback without duplicate reviews | As a Customer I want to leave at most one rating and review for my completed order so that the restaurant gets clear feedback without duplicate reviews | Medium | 5
13.0 | Promotions: create codes; validate & apply at checkout | Restaurant manager | create promotions and promo codes for customers | I can run marketing campaigns | As a Restaurant manager I want to create promotions and promo codes for customers so that I can run marketing campaigns | Medium | 5
14.0 | Analytics: trends, preferences, sales | Restaurant owner | view analytics about sales, trends, and customer preferences | I can make better business decisions | As a Restaurant owner I want to view analytics about sales, trends, and customer preferences so that I can make better business decisions | Low | 8
15.0 | Promotions: create codes; validate & apply at checkout | Customer | enter a promo code during checkout | a valid discount is applied to my order | As a Customer I want to enter a promo code during checkout so that a valid discount is applied to my order | High | 3
16.0 | Promotions: create codes; validate & apply at checkout | Customer | see a clear message when a promo code is invalid or expired | I can correct the code or continue without the discount | As a Customer I want to see a clear message when a promo code is invalid or expired so that I can correct the code or continue without the discount | High | 2
17.0 | Payment processing (multiple methods, transaction status, failures) | Customer | retry payment after a failure | I can complete my order without starting over | As a Customer I want to retry payment after a failure so that I can complete my order without starting over | High | 3
18.0 | Order record: customer link, total price, status, tracking #, order type | Customer | see my order total before paying | I agree to the final amount before checkout completes | As a Customer I want to see my order total before paying so that I agree to the final amount before checkout completes | High | 3
19.0 | Order record: customer link, total price, status, tracking #, order type | Guest customer | have my order linked to my name, phone, and address | staff can prepare and deliver my order correctly | As a Guest customer I want to have my order linked to my name, phone, and address so that staff can prepare and deliver my order correctly | High | 2
20.0 | Staff & cook: update order status | Staff member | update order status (e.g., received, preparing, ready) | customers see accurate progress on their order | As a Staff member I want to update order status (e.g., received, preparing, ready) so that customers see accurate progress on their order | Medium | 3
21.0 | Staff & cook: update order status | Chef | update order status from the kitchen view | customers and front-of-house know when food is ready | As a Chef I want to update order status from the kitchen view so that customers and front-of-house know when food is ready | Medium | 3
22.0 | Documentation & staff training materials | Restaurant owner | access onboarding and training materials for staff | new hires learn processes consistently | As a Restaurant owner I want to access onboarding and training materials for staff so that new hires learn processes consistently | Low | 3
23.0 | Analytics: trends, preferences, sales | Restaurant owner | filter analytics by date range or category | I can answer specific business questions quickly | As a Restaurant owner I want to filter analytics by date range or category so that I can answer specific business questions quickly | Low | 3
TOTAL | [6 empty] | 100